Low Hack 2026 - Strategic Report

Comprehensive Pre-Requisites, Timeline & Deliverables

Event Date: April 18-19, 2026
Organizers: TrueChange & Siemens Digital Industries Software
Platform: Mendix (Low-Code)
Prize Pool: R$ 16,000 total

Executive Summary

Low Hack 2026 is a 48-hour online hackathon focused on leveraging Mendix low-code platform and AI to develop innovative solutions for sustainable industrial practices. This report provides a complete strategic framework covering all prerequisites, critical timeline milestones, and deliverables required for successful participation and execution.

Event Focus: ODS 9 (Industry, Innovation & Infrastructure) and ODS 12 (Responsible Consumption & Production)

Part 1: Pre-Requisites & Requirements

1.1 Participant Prerequisites

Technical Skills (NOT Required)

- No programming experience necessary

- Open to all professional backgrounds

Recommended Skills

- Problem-solving and creative thinking

- Basic digital platform navigation

- Understanding of sustainability concepts

- Collaborative teamwork

Diverse Team Backgrounds Welcome

- Web & Mobile Development

- Graphic & Digital Design

- Business Management

- Communication & Marketing

- Data Analysis

- UX/UI Design

1.2 Platform & Technical Requirements

Mendix Platform Access

- Free trial account (available via Mendix)

- No prior Mendix experience required

- Cloud-based access (no local installation needed)

- Compatible with: Windows, macOS, Linux

System Requirements

- Internet connection (stable, minimum 5 Mbps recommended)

- Modern web browser (Chrome, Firefox, Safari, Edge)

- Minimum 4GB RAM on development machine

- 2GB free disk space for Mendix Studio downloads

AI Integration Preparation

- Basic understanding of AI/ML concepts helpful

- Access to API documentation for AI services

- Familiarity with data preparation fundamentals

1.3 Administrative Requirements

Registration Prerequisites

- Valid email address

- Account on Desafios.hackathonbrasil.com.br

- Team lead designation (1 per team)

- Team size: 1-5 members (verified at event start)

Documentation Needed

- Government ID or student document

- Team member names and emails

- Project description outline (max 300 characters)

Communication Channels

- Discord server access (released April 15)

- WhatsApp group participation (optional but recommended)

- Email notifications enabled

1.4 Knowledge & Resource Prerequisites

Mendix Low-Code Platform

- Official tutorials: Mendix Academy resources

- Documentation: Platform capabilities and limitations

- Use case libraries: Industry examples

- Community forums: Peer support

Sustainability & Industry Focus

- ODS 9 guidelines and targets

- ODS 12 sustainable production principles

- Industry 4.0 concepts

- Circular economy models

AI Application in Industry

- AI use cases in manufacturing

- Data optimization principles

- Process automation benefits

- Ethical AI considerations

Part 2: Complete Timeline & Milestones

Critical Dates & Deadlines

| Milestone | Date | Time | Action | Responsible |
| --- | --- | --- | --- | --- |
| Hackathon Opens | Now | - | Registration opens | Participants |
| DEADLINE 1 | April 15, 2026 | 23:59 | Registration closes | Participants |
| Discord Launch | April 15, 2026 | 17:00 | Team formation begins | All |
| DEADLINE 2 | April 17, 2026 | 23:59 | Final team roster due | Team Lead |
| Event Start | April 18, 2026 | 09:00 | Day 1 kickoff | Organizers |
| DEADLINE 3 | April 18, 2026 | 22:00 | End of Day 1 work | N/A |
| Event Continues | April 19, 2026 | 00:00 | Day 2 begins | N/A |
| DEADLINE 4 | April 19, 2026 | 22:00 | Project submission deadline | Participants |
| Winners Announced | April 24, 2026 | 18:00 | Results published | Organizers |

Part 3: Pre-Event Timeline (March 28 - April 17)

Week 1: March 28 - April 3 (Foundation Phase)

Phase Duration: 7 days

Week 1 Deliverables

- [ ] Team formation (recruit 2-4 additional members)

- [ ] Skill assessment of team members

- [ ] Mendix account creation for all members

- [ ] Mendix Academy basic tutorials completion (estimated 4-6 hours)

- [ ] Initial project concept brainstorm (3-5 ideas)

Week 1 Milestones

| Date | Deliverable | Owner |
| --- | --- | --- |
| Mar 28-30 | Team assembled | Team Lead |
| Mar 31-Apr 2 | Mendix training completed | All members |
| Apr 2-3 | 3+ concepts drafted | Design Lead |

Week 1 Success Criteria

- ✓ All team members have Mendix accounts

- ✓ Team communication channels established (Discord/WhatsApp)

- ✓ At least 2 viable project concepts identified

- ✓ Team roles assigned (Developer, Designer, Product Manager, etc.)

Week 2: April 4 - April 10 (Preparation Phase)

Phase Duration: 7 days

Week 2 Deliverables

- [ ] Project idea validation against ODS 9 & 12

- [ ] Mendix platform deep-dive training (case studies, examples)

- [ ] Sustainability research completed

- [ ] AI integration methods researched

- [ ] Technical architecture outline drafted

- [ ] Team roles finalized

- [ ] Development environment setup

Week 2 Milestones

| Date | Deliverable | Owner |
| --- | --- | --- |
| Apr 4-6 | Sustainability research | Product Manager |
| Apr 6-8 | AI research & documentation | Lead Developer |
| Apr 8-9 | Technical design document | Architect |
| Apr 9-10 | Environment setup complete | All members |

Week 2 Success Criteria

- ✓ 1 final project concept selected and documented

- ✓ Alignment with ODS 9 & ODS 12 verified

- ✓ Technical approach defined (components, APIs, integrations)

- ✓ All team members comfortable with Mendix platform

- ✓ Team testing environment ready

Week 3: April 11 - April 17 (Final Prep Phase)

Phase Duration: 7 days

Week 3 Deliverables

- [ ] Advanced Mendix training completion

- [ ] API documentation reviewed (Mendix, AI services)

- [ ] Data models designed

- [ ] UI/UX wireframes completed

- [ ] Development sprint plan created

- [ ] Risk assessment & contingency plans

- [ ] Final team coordination sync

Week 3 Milestones

| Date | Deliverable | Owner |
| --- | --- | --- |
| Apr 11-12 | API integration planning | Lead Developer |
| Apr 12-13 | UI mockups completed | Designer |
| Apr 13-14 | Sprint plan finalized | Project Manager |
| Apr 15 | Discord opened | Organizers |
| Apr 15 | Discord team formation | Team Lead |
| Apr 16-17 | Final prep & testing | All members |
| Apr 17 | 23:59 - Team roster deadline | Team Lead |

Week 3 Success Criteria

- ✓ Team roster submitted by April 17, 23:59

- ✓ Discord team channel active and organized

- ✓ Development plan with 48-hour breakdown ready

- ✓ All team members synced on expectations

- ✓ Backup plans for technical issues prepared

- ✓ Team member availability confirmed for April 18-19

Part 4: Event Timeline (April 18-19)

Day 1: April 18, 2026 (36 Hours to Milestone)

09:00 - Kickoff (1 hour)

- Event brief by organizers

- Challenge deep-dive

- Q&A session

- Deliverable: Understanding of exact requirements

10:00-14:00 - Design Phase (4 hours)

- Project refinement

- UI/UX finalization

- Data model confirmation

- Deliverable: Final design documents ready for development

14:00-22:00 - Development Sprint 1 (8 hours)

- Core functionality implementation

- API integration setup

- Database configuration

- Progress check-ins (hourly recommended)

- Deliverable: 40-50% of MVP features functional

22:00 - End of Day 1 (Suggested Rest)

- Team sync & sleep rotation begins

- Keep 1 team member awake for progress tracking

- Deliverable: Day 1 wrap-up documentation

Day 2: April 19, 2026 (26 Hours Remaining)

00:00-09:00 - Development Sprint 2 (9 hours)

- Continued feature implementation

- AI integration completion

- Testing and bug fixes

- Deliverable: 70-80% of MVP features complete

09:00-18:00 - Development Sprint 3 (9 hours)

- Feature completion

- Full system testing

- Performance optimization

- UI/UX refinement

- Deliverable: 95%+ MVP features complete

18:00-21:00 - Finalization (3 hours)

- Bug fixes and polish

- Demo presentation preparation

- Documentation completion

- Deliverable: Production-ready prototype

21:00-22:00 - Submission Preparation (1 hour)

- Final video/demo recording

- README and technical documentation

- Source code organization

- DEADLINE 4: 22:00 - Final Submission

22:00 - SUBMISSION DEADLINE

All deliverables must be uploaded by this time

Part 5: Deliverables Checklist

Pre-Event Deliverables (Due Before April 18)

- [ ] Team roster finalized (by April 17, 23:59)

- [ ] Project concept document (5-10 pages)

- [ ] Technical architecture diagram

- [ ] UI/UX wireframes or mockups

- [ ] Data model documentation

- [ ] Mendix development environment configured

- [ ] API integration plans documented

- [ ] Risk management plan

Event Deliverables (Due April 19, 22:00)

Required Submissions

- [ ] Working Mendix Application - Functional prototype deployed

- [ ] Source Code - All code and configuration files

- [ ] Technical Documentation (5-10 pages minimum)

  - Architecture overview

  - Technology stack

  - API integrations used

  - Database design

  - Deployment instructions

- [ ] README File - Quick start guide for judges

- [ ] Demo Video (3-5 minutes)

  - Feature walkthrough

  - Problem solved explanation

  - Impact demonstration

  - Team member introductions

- [ ] Presentation Slides (10-15 slides)

  - Challenge understanding

  - Solution overview

  - Technical approach

  - Results & metrics

  - Sustainability impact

Recommended Submissions

- [ ] User Guide - How to use the application

- [ ] Product Roadmap - Future development plans

- [ ] Business Model - Monetization/scaling approach

- [ ] Screenshots & Mockups - Visual documentation

- [ ] Test Cases - Quality assurance documentation

Post-Event Deliverables

- [ ] Judges feedback review (April 24+)

- [ ] Project showcase participation (if finalist)

- [ ] Certificate of participation (automatic)

- [ ] Badge Siemens (if top 3)

Part 6: Resource Allocation Plan

Team Structure (Recommended)

| Role | Count | Responsibilities |
| --- | --- | --- |
| Lead Developer | 1 | Mendix implementation, API integration, architecture decisions |
| Designer/UX | 1 | UI/UX design, wireframes, user experience optimization |
| Product Manager | 1 | Feature prioritization, scope management, requirements |
| Data Engineer | 1 | Database design, AI data preparation, integration |
| Documentation | 1 | README, technical docs, presentation slides |

Flexible Configuration: Roles can be combined; team size 1-5 members allowed.

Time Allocation (48-Hour Event)

Development: 32 hours (67%)
Testing/QA: 8 hours (17%)
Documentation: 4 hours (8%)
Presentation: 4 hours (8%)

Resource Requirements

Software (All Free)

- Mendix Studio (trial account)

- GitHub/GitLab (version control)

- Figma (design - free tier)

- Discord (communication)

- Any APIs used (verify free tier availability)

Hardware

- Development computers (1 per developer minimum)

- Stable internet connection

- Backup internet source (mobile hotspot)

Documentation Tools

- Google Docs/Notion (guides)

- Canva (presentation design)

- OBS Studio (demo video recording)

Part 7: Success Metrics & KPIs

Product Metrics

- Functionality Score: 80%+ features working

- Performance: App loads in <2 seconds

- Code Quality: Clean, documented, modular code

- UI/UX Rating: Intuitive, accessible interface

- AI Integration: Active AI component in solution

Business Metrics

- Problem-Solution Fit: Clear alignment with ODS 9/12

- Innovation Score: Novel approach or unique perspective

- Scalability: Solution applicable to real-world industry scenario

- Sustainability Impact: Quantifiable environmental benefit

- Feasibility: Realistic implementation timeline

Judging Criteria (Expected Weights)

- Technical Excellence: 25%

- Innovation & Creativity: 25%

- Sustainability Impact: 20%

- Presentation & Documentation: 15%

- Team Execution: 15%

Part 8: Risk Management & Contingencies

High-Risk Areas

| Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| Team member unavailability | Medium | High | Backup members identified |
| Mendix technical issues | Medium | Medium | Pre-event environment testing |
| Scope creep | High | High | Daily standup & scope control |
| API integration failures | Medium | High | Multiple API options researched |
| Data quality issues | Medium | Medium | Pre-prepared test datasets |
| Submission technical errors | Low | High | Pre-submission dry run |
| Internet connectivity loss | Low | High | Mobile hotspot backup |

Contingency Plans

If Mendix platform fails:

- Switch to alternative low-code platform (OutSystems, etc.)

- Notify organizers immediately

- Request deadline extension

If team member leaves:

- Redistribute workload among remaining members

- Focus on MVP only (cut nice-to-have features)

- Adjust roles accordingly

If API integration fails:

- Use mock data/hardcoded responses

- Prepare fallback integration method

- Document issue for judges

If submission fails at deadline:

- Have backup submission method ready

- Verify upload status 30 minutes before deadline

- Contact organizers immediately if issues arise

Part 9: Execution Checklist by Phase

Pre-Event Phase (March 28 - April 17)

- [ ] Week 1: Team formed & Mendix training started

- [ ] Week 2: Project concept finalized & research complete

- [ ] Week 3: Development environment ready & team synced

- [ ] April 15: Discord server access confirmed

- [ ] April 17: Team roster submitted before 23:59

- [ ] April 17: All team members confirm availability for April 18-19

Event Phase (April 18-19)

- [ ] Apr 18, 09:00: Attend kickoff meeting

- [ ] Apr 18, 10:00: Design phase finalized

- [ ] Apr 18, 14:00: Development begins

- [ ] Apr 18, 22:00: Day 1 wrap-up & rest rotation

- [ ] Apr 19, 09:00: Development continues

- [ ] Apr 19, 18:00: Feature implementation complete

- [ ] Apr 19, 21:00: Demo & documentation ready

- [ ] Apr 19, 21:45: Final submission check

- [ ] Apr 19, 22:00: All files uploaded before deadline

Post-Event Phase (April 24+)

- [ ] Receive participant certificate

- [ ] Review judge feedback

- [ ] If finalist: Prepare showcase presentation

- [ ] Document learnings for future improvements

Part 10: Strategic Recommendations

For Maximum Competition Success

- Deep Domain Focus: Master one specific industry problem rather than attempting broad solutions

- AI Strategic Use: Make AI integral to solution, not just added feature

- Sustainability Quantification: Include metrics (e.g., "reduces waste by X%", "saves Y resources")

- MVP Clarity: Focus 80% of effort on core features; polish remaining 20%

- Presentation Excellence: Compelling story beats technical complexity

- Early Testing: Identify critical issues by Apr 18 evening, Day 1

- Documentation Priority: Complete docs by Apr 19 18:00 for error-free submission

- Backup Everything: Version control, cloud storage, hardware redundancy

Resource Optimization

- Pre-event investment: 20-30 hours of prep work saves 10+ hours during event

- Role clarity: Clear responsibilities prevent overlap and confusion

- Communication protocol: 2-hour standup cycles recommended during 48-hour sprint

- Sleep rotation: Assign time slots; exhausted developers produce bugs

Conclusion & Next Steps

Immediate Actions (This Week)

- Recruit team members (aim for 3-4 people)

- Create project collaboration space (Discord/Notion)

- Initiate Mendix accounts for all members

- Schedule kick-off team meeting

Week 1-2 Actions

- Complete Mendix Academy training

- Research ODS 9 & 12 requirements in depth

- Brainstorm 5-10 project ideas

- Select and validate final concept

Week 3 Actions

- Finalize technical architecture

- Create development sprint plan

- Prepare pre-event environment

- Conduct final team coordination

Appendix: Useful Resources

Mendix Platform

- Academy: academy.mendix.com

- Documentation: docs.mendix.com

- Community: community.mendix.com

- Marketplace: appstore.home.mendix.com

Sustainability Frameworks

- ODS 9: https://sdgs.un.org/goals/goal9

- ODS 12: https://sdgs.un.org/goals/goal12

- Industry 4.0: ISO/IEC 40001 standards

Development Tools

- Git/GitHub: github.com (version control)

- Figma: figma.com (design)

- Discord: discord.com (communication)

- Notion: notion.so (documentation)

Communication Channels

- WhatsApp Group: https://chat.whatsapp.com/LOMPBfNPmS5Glh6uBR925y

- Discord: Released April 15 (team formation)

- Organizer Email: hackathonbrasil.com.br (support)

Event Information

- Official Website: hackathonbrasil.com.br/low-hack

- Regulation Document: Available on registration page

- Prize Pool: R$ 16,000 (1st: R$8,000 | 2nd: R$5,000 | 3rd: R$3,000)

Document Version: 1.0
Last Updated: March 28, 2026
Next Review: April 17, 2026
Prepared For: Low Hack 2026 Participants